## RFB
Request for Bids
Activity Reference No. / Description: | In-Process | Loan / Credit No. | Component | Review Type | Category | Market Approach | Prequalification (Y/N) | Procurement Process | Evaluation Options | Estimated Amount (US$) | High SEA/SH Risk | Procurement Document Type | Process Status | Activity Status | Draft Pre-qualification Documents |  | Specific Procurement Notice |  | Amendments to Pre-qualification Documents | Opening / Minutes of Pre-qualification |  | Pre-qualification Evaluation Report |  | Draft Bidding Documents |  | Specific Procurement Notice |  | Invitation to Providers |  | Amendments to Bidding Documents | Bid Submission / Opening / Minutes |  | Bid Evaluation Report and Recommendation for Award |  | Notification of Intention of Award |  | Signed Contract |  | Contract Amendments | Contract Completion |  | Contract Termination
[15 empty] | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Actual
BJ-COE-EIE BENIN-215964-GO-RFB / Acquisition de matériels roulants pour les sorties pédagogiques, les supervisions, les visites d'entreprises et la coordination du centre | No | IDA-65090 | Establishing New and Scaling up Well-performing existing Africa Centers of Excellence for Development Impact | Prior | Goods | Open - National | N | Single Stage One Envelope |  | 150000 |  |  | Not Submitted | Nouveau | [9 empty] | 2021/04/07 |  | 2021/04/12 |  |  |  |  | 2021/05/24 |  | 2021/06/23 |  | 2021/07/07 |  | 2021/07/28 |  |  | 2022/01/24

## RFQ
Request for Quotations
Activity Reference No. / Description: | In-Process | Loan / Credit No. | Component | Review Type | Category | Market Approach | Estimated Amount (US$) | High SEA/SH Risk | Procurement Document Type | Process Status | Activity Status | Draft Request for Quotations |  | Specific Procurement Notice |  | Invitation to Supplier / Contractor |  | Amendments to Request for Quotations | Receive Quotations |  | Comparison of Quotations |  | Notification of Intention of Award |  | Signed Contract |  | Contract Amendments | Contract Completion |  | Contract Termination
[12 empty] | Planned | Actual | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Actual
BJ-COE-EIE BENIN-215968-GO-RFQ / Acquisition d'un matériel d'énergie de secours et fibre optique: abonnement, prise en compte de l'étude préliminaire et mutualisation | No | IDA-65090 | Establishing New and Scaling up Well-performing existing Africa Centers of Excellence for Development Impact | Prior | Goods | Open - National | 55000 |  |  | Not Submitted | Nouveau | 2021/03/01 |  | 2021/03/06 |  | 2021/03/06 |  |  | 2021/03/20 |  | 2021/03/27 |  | 2021/04/10 |  | 2021/05/01 |  |  | 2021/10/28
BJ-COE-EIE BENIN-215946-NC-RFQ / Recrutement d'un prestataire pour la conception et l'édition des postes d'appels à candidature | No | IDA-65090 | Establishing New and Scaling up Well-performing existing Africa Centers of Excellence for Development Impact | Post | Non-consulting Services | Limited | 5000 |  |  | Not Submitted | Nouveau | 2021/02/18 | [6 empty] | 2021/03/09 |  | 2021/03/16 |  | 2021/03/30 |  | 2021/04/20 |  |  | 2021/10/17
BJ-COE-EIE BENIN-215955-GO-RFQ / Acquisition de matériels informatiques pour le fonctionnement du centre et pour l'équipement de la structure d'assurance qualité dans la formation du CoE.EIE | No | IDA-65090 | Establishing New and Scaling up Well-performing existing Africa Centers of Excellence for Development Impact | Prior | Goods | Limited | 35000 |  |  | Not Submitted | Nouveau | 2021/02/15 | [6 empty] | 2021/03/06 |  | 2021/03/13 |  | 2021/03/27 |  | 2021/04/17 |  |  | 2021/10/14
BJ-COE-EIE BENIN-216008-GO-RFQ / Acquisition de matériel de protection contre le covid-19 | No | IDA-65090 | Establishing New and Scaling up Well-performing existing Africa Centers of Excellence for Development Impact | Post | Goods | Limited | 3500 |  |  | Not Submitted | Nouveau | 2021/04/15 | [6 empty] | 2021/05/04 |  | 2021/05/11 |  | 2021/05/25 |  | 2021/06/15 |  |  | 2021/12/12
BJ-COE-EIE BENIN-215980-GO-RFQ / Acquisition de fournitures de bureaux et consommables pour le fonctionnement du collège | No | IDA-65090 | Establishing New and Scaling up Well-performing existing Africa Centers of Excellence for Development Impact | Post | Goods | Limited | 10000 |  |  | Not Submitted | Nouveau | 2021/02/01 | [6 empty] | 2021/02/20 |  | 2021/02/27 |  | 2021/03/13 |  | 2021/04/03 |  |  | 2021/09/30
BJ-COE-EIE BENIN-215987-NC-RFQ / Recrutement d'un prestataire pour la maintenance des matériels informatiques et électriques | No | IDA-65090 | Establishing New and Scaling up Well-performing existing Africa Centers of Excellence for Development Impact | Post | Non-consulting Services | Limited | 10000 |  |  | Not Submitted | Nouveau | 2021/03/08 | [6 empty] | 2021/03/27 |  | 2021/04/03 |  | 2021/04/17 |  | 2021/05/08 |  |  | 2021/11/04
BJ-COE-EIE BENIN-215952-NC-RFQ / Recrutement d'une compagnie d'assurance pour l'assurance vie des étudiants étrangers | No | IDA-65090 | Establishing New and Scaling up Well-performing existing Africa Centers of Excellence for Development Impact | Post | Non-consulting Services | Limited | 15000 |  |  | Not Submitted | Nouveau | 2021/03/01 | [6 empty] | 2021/03/20 |  | 2021/03/27 |  | 2021/04/10 |  | 2021/05/01 |  |  | 2021/10/28
BJ-COE-EIE BENIN-215984-NC-RFQ / Recrutement d'un prestataire pour assurer l'interconnexion des centres d'excellence du Bénin | No | IDA-65090 | Establishing New and Scaling up Well-performing existing Africa Centers of Excellence for Development Impact | Prior | Non-consulting Services | Open - National | 15000 |  |  | Not Submitted | Nouveau | 2021/06/01 |  | 2021/06/06 |  | 2021/06/06 |  |  | 2021/06/20 |  | 2021/06/27 |  | 2021/07/11 |  | 2021/08/01 |  |  | 2022/01/28

## DIR
Direct Selection
Activity Reference No. / Description: | In-Process | Loan / Credit No. | Component | Review Type | Procurement Category | Evaluation Options | Estimated Amount (US$) | High SEA/SH Risk | Procurement Document Type | Process Status | Activity Status | Justification for Direct Procurement |  | Invitation to Supplier / Contractor |  | Draft Contract |  | Notification of Intention of Award |  | Signed Contract |  | Contract Amendments | Contract Completion |  | Contract Termination
[12 empty] | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Actual
BJ-COE-EIE BENIN-215983-NC-DIR / Renforcement de la bibliothèque numérique par la souscription à des ressources en ligne | No | IDA-65090 | Establishing New and Scaling up Well-performing existing Africa Centers of Excellence for Development Impact | Prior | Non-consulting Services | Direct | 10000 |  |  | Not Submitted | Nouveau | 2021/03/01 |  | 2021/03/06 |  | 2021/03/06 |  | 2021/03/20 |  | 2021/04/10 |  |  | 2021/10/07
BJ-COE-EIE BENIN-215986-GO-DIR / Acquisition de carburant pour le fonctionnement du collège | No | IDA-65090 | Establishing New and Scaling up Well-performing existing Africa Centers of Excellence for Development Impact | Post | Goods | Direct | 20000 |  |  | Not Submitted | Nouveau | 2021/02/08 |  | 2021/02/13 |  | 2021/02/13 |  | 2021/02/27 |  | 2021/03/20 |  |  | 2021/09/16

## QCBS - FBS - LCS
Quality and Cost Based Selection (QCBS), Fixed Budget Based Selection (FBBS), Least Cost Based Selection (LCBS)
Activity Reference No. / Description: | In-Process | Loan / Credit No. | Component | Review Type | Category | Market Approach | Estimated Amount (US$) | Process Status | Activity Status | Terms of Reference |  | Expression of Interest |  | Evaluation of Expression of Interest and Short List of Consultants |  | Short List and Draft Request for Proposals |  | Request for Proposals as Issued |  | Amendments to Request for Proposals |  | Opening of Technical Proposals / Minutes |  | Evaluation of Technical Proposals |  | Opening of Financial Proposals / Minutes |  | Combined Evaluation Report and Draft Negotiated Contract |  | Notification of Intention of Award |  | Signed Contract |  | Contract Amendments | Contract Completion |  | Contract Termination
[10 empty] | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Actual
BJ-COE-EIE BENIN-215985-CS-LCS / Recrutement conjoint avec les autres centres, d'un cabinet pour l'élaboration du plan comptable des projets CEA | No | IDA-65090 | Establishing New and Scaling up Well-performing existing Africa Centers of Excellence for Development Impact | Prior | Consultant Services | Open - National | 3350 | Not Submitted | Nouveau | 2021/02/01 |  | 2021/02/22 |  | 2021/03/24 |  | 2021/04/07 |  |  |  | 2021/04/07 |  | 2021/05/05 |  | 2021/06/04 |  | 2021/06/18 |  | 2021/07/09 |  | 2021/07/23 |  | 2021/08/13 |  |  | 2022/02/09
BJ-COE-EIE BENIN-215959-CS-LCS / Recrutement d'un cabinet pour la conception des plans architecturaux et techniques d'un batiment à usage polyvalent de type R+2 au profit de l'EPAC | No | IDA-65090 | Establishing New and Scaling up Well-performing existing Africa Centers of Excellence for Development Impact | Prior | Consultant Services | Open - National | 50000 | Not Submitted | Nouveau | 2021/04/05 |  | 2021/04/26 |  | 2021/05/26 |  | 2021/06/09 |  |  |  | 2021/06/09 |  | 2021/07/07 |  | 2021/08/06 |  | 2021/08/20 |  | 2021/09/10 |  | 2021/09/24 |  | 2021/10/15 |  |  | 2022/04/13
BJ-COE-EIE BENIN-215977-CS-LCS / Recrutement d'un cabinet pour réaliser l'audit financier et de passation des marchés du centre | No | IDA-65090 | Establishing New and Scaling up Well-performing existing Africa Centers of Excellence for Development Impact | Prior | Consultant Services | Open - International | 10000 | Not Submitted | Nouveau | 2021/02/01 |  | 2021/02/22 |  | 2021/03/24 |  | 2021/04/07 |  |  |  | 2021/04/07 |  | 2021/05/05 |  | 2021/06/04 |  | 2021/06/18 |  | 2021/07/09 |  | 2021/07/23 |  | 2021/08/13 |  |  | 2022/02/09
BJ-COE-EIE BENIN-215963-CS-LCS / Recrutement d'un cabinet pour réaliser l'étude en vue d'équiper les laboratoires de recherche | No | IDA-65090 | Establishing New and Scaling up Well-performing existing Africa Centers of Excellence for Development Impact | Prior | Consultant Services | Open - International | 8000 | Not Submitted | Nouveau | 2021/05/03 |  | 2021/05/24 |  | 2021/06/23 |  | 2021/07/07 |  |  |  | 2021/07/07 |  | 2021/08/04 |  | 2021/09/03 |  | 2021/09/17 |  | 2021/10/08 |  | 2021/10/22 |  | 2021/11/12 |  |  | 2022/05/11
BJ-COE-EIE BENIN-215961-CS-LCS / Recrutement d'un cabinet pour réaliser l'étude technique pour le renforcement des capacités en TICE | No | IDA-65090 | Establishing New and Scaling up Well-performing existing Africa Centers of Excellence for Development Impact | Prior | Consultant Services | Open - National | 10000 | Not Submitted | Nouveau | 2021/04/05 |  | 2021/04/26 |  | 2021/05/26 |  | 2021/06/09 |  |  |  | 2021/06/09 |  | 2021/07/07 |  | 2021/08/06 |  | 2021/08/20 |  | 2021/09/10 |  | 2021/09/24 |  | 2021/10/15 |  |  | 2022/04/13
BJ-COE-EIE BENIN-215981-CS-LCS / Recrutement d'un cabinet pour le développement d'un outil automatique de suivi évaluation pour les centres d'excellence | No | IDA-65090 | Establishing New and Scaling up Well-performing existing Africa Centers of Excellence for Development Impact | Prior | Consultant Services | Open - National | 9000 | Not Submitted | Nouveau | 2021/03/01 |  | 2021/03/22 |  | 2021/04/21 |  | 2021/05/05 |  |  |  | 2021/05/05 |  | 2021/06/02 |  | 2021/07/02 |  | 2021/07/16 |  | 2021/08/06 |  | 2021/08/20 |  | 2021/09/10 |  |  | 2022/03/09

## CDS
Consultant Direct Selection (CDS)
Activity Reference No. / Description: | In-Process | Loan / Credit No. | Component | Review Type | Category | Market Approach | Estimated Amount (US$) | Process Status | Activity Status | Terms of Reference |  | Justification for Direct Selection |  | Invitation to Identified/Selected Consultant |  | Amendments to Terms of Reference |  | Draft Negotiated Contract |  | Notification of Intention of Award |  | Signed Contract |  | Contract Amendments | Contract Completion |  | Contract Termination
[10 empty] | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Actual
BJ-COE-EIE BENIN-215970-CS-LCS / Acquisition d'un logiciel de gestion des finances, du patrimoine, de l'administration de l'information et de la communication | No | IDA-65090 | Establishing New and Scaling up Well-performing existing Africa Centers of Excellence for Development Impact | Prior | Consultant Services | Direct | 30000 | Not Submitted | Nouveau | 2021/03/08 |  | 2021/03/13 |  | 2021/03/18 |  | 2021/03/18 |  | 2021/04/17 |  | 2021/05/01 |  | 2021/05/22 |  |  | 2021/11/18